## 99 Gun Master Plan
ISLAMVY - 99 GUNLUK 3M INDIRME SAVAS PLANI
GUN | TARIH | FAZ | GUNLUK HEDEF | ANA GOREV | DETAYLI AKSIYONLAR | BUTÇE ($) | METRIK
-7 | 08-Feb | Lansman Hazirlik | App Store Optimize | ASO Kurulum | App Store screenshots hazirla (10 adet/dil). Keywords research yap. Description yaz 4 dilde. Video preview hazirla. Competitor analizi. | - | Keyword listesi
-6 | 09-Feb | Lansman Hazirlik | Sosyal Medya Setup | Hesap Acma | Instagram: @islamvy.app @islamvy.tr @islamvy.ar @islamvy.id ac. TikTok: ayni handlelar. Twitter/X: @islamvyapp. YouTube: Islamvy Official ac. Bio: Launching Feb 15 | - | 8 hesap acik
-5 | 10-Feb | Lansman Hazirlik | Content Bank | Video Hazirlik | 20 teaser video cek (15-30sn). AI Dream showcase. Community prayer gorsel. Ramadan countdown. Canva Pro al | 13 | 20 video ready
-4 | 11-Feb | Lansman Hazirlik | Influencer Seed | Liste Cikar | Instagram 50 mikro-influencer (5K-50K). TikTok 50 creator (10K-100K). Excel organize et. DM template hazirla. Hedef: 20% response | - | 100 influencer list
-3 | 12-Feb | Lansman Hazirlik | Beta Test | Ilk Kullanicilar | Aile 20 kisi indir. Arkadaslar 30 kisi. WhatsApp gruplari (5 grup). Bug report form kur. 5 yildiz review hazirla | - | 50 beta user
-2 | 13-Feb | Lansman Hazirlik | PR Hazirlik | Basin Bildirisi | Press kit hazirla. TechCrunch VentureBeat email bul. Lokal medya Turkiye 10 Endonezya 10 UAE 5. Pitch email yaz. Product Hunt hesap ac | - | Press kit ready
-1 | 14-Feb | Lansman Hazirlik | Final Check | Son Kontrol | App Store submission check. Push notification test. Payment RevenueCat test. Analytics Firebase Adjust kur. Influencerlara yarin reminder. Countdown baslat | - | All systems go
0 | 15-Feb | LANSMAN | Gun 1 | Go Live | 06:00 App live. 07:00 Product Hunt. 08:00 Social media blitz. 09:00 Beta notify. 10:00 Influencer affiliate links. 12:00 Reddit. 15:00 Ilk 100 kutla. 18:00 IG Live QA. 20:00 Metrics | 50 | 500 indirme
1 | 16-Feb | LANSMAN | Momentum | Ilk Dalga | 08:00 PH commentlere cevap. 09:00 Ilk 5 review screenshot. 11:00 TikTok 3 video. 14:00 FB 20 grup. 16:00 WhatsApp status. 18:00 Influencer check. 20:00 Discord 10 server | - | 1,000 indirme
2 | 17-Feb | LANSMAN | Amplify | Ses Getir | 07:00 Press kit 50 medya. 09:00 Twitter thread How We Built. 11:00 LinkedIn founder story. 13:00 IG Reels 5x. 15:00 Ilk hatim baslat. 17:00 Community 10 dua seed. 19:00 TikTok duet challenge | - | 2,500 indirme
3 | 18-Feb | LANSMAN | Viral Push | Gaz Ver | 08:00 Ilk viral video repost. 10:00 Hacker News Show HN. 12:00 Quora 5 soru cevap. 14:00 Medium blog journey. 16:00 YouTube 10 short. 18:00 Influencer ode. 20:00 Giveaway 3x Premium | 100 | 5,000 indirme
4 | 19-Feb | Ilk Hafta | Build | Gun 5 | 50 influencer outreach gunluk. Barter: Premium + Dashboard. Brief gonder. TikTok challenge #IslamvyDreams. IG story template. Response track | 20 | 8K indirme
5 | 20-Feb | Ilk Hafta | Build | Gun 6 | Community 50 seed post. Ilk 5 hatim organize. Engagement contest en cok amin 1ay Premium. Telegram ac. Discord kur. WhatsApp community | - | 12K indirme
6 | 21-Feb | Ilk Hafta | Build | Gun 7 | TikTok 10 video batch. Instagram 5 Reels + 3 carousel. YouTube 15 shorts. UGC repost 10x. Reddit AMA. Twitter Space host | - | 15K indirme
7 | 22-Feb | Ilk Hafta | Scale | Gun 8 | 20 podcast basvur. Lokal TV pitch. Tech blogger eksklusif. 10K in 1 week PR. Case study. Affiliate Islamic sites | - | 20K indirme
8 | 23-Feb | Ilk Hafta | Scale | Gun 9 | Referral bonus 2x limited. Leaderboard baslat. Top 10: Lifetime Unlimited. In-app banner Invite Win. Push referral reminder. Email share | - | 25K indirme
9 | 24-Feb | Ilk Hafta | Scale | Gun 10 | PH Featured Update. Reddit r/startups. IndieHackers milestone. Twitter viral metrics. LinkedIn founder update. Community celebration | - | 30K indirme
10 | 25-Feb | Ilk Hafta | Scale | Gun 11 | Metrics deep dive: hangi kanal calisdi. Influencer ROI. En viral content. Retention Day 1-3-7. Bug priority. Hafta 2 plan. Team call | - | 35K indirme
11 | 26-Feb | Hafta 2 Scale | Paid Start | FB Ads Baslat | FB Ads Manager setup. Campaign: Conversion Registration. Muslim interests Ramadan prep. 3 video + 2 carousel. Butce 20$/gun. AB test. Pixel check | 20 | 40K indirme
12 | 27-Feb | Hafta 2 Scale | Google UAC | Android Push | Google Ads UAC baslat. 5 video + 10 image asset. Butce 15$/gun. Indonesia Pakistan Bangladesh. Conversion: Registration. CPI track | 15 | 47K indirme
13 | 28-Feb | Hafta 2 Scale | Apple Search | iOS Optimize | Apple Search Ads setup. Exact: prayer times quran app. Broad: Islamic lifestyle. Butce 10$/gun. Turkiye UAE Saudi. Creative test. TTR optimize | 10 | 55K indirme
14 | 01-Mar | Hafta 2 Scale | Influencer Wave 2 | Macro Basla | 10 macro influencer 50K-500K. Odeme 100-300$/post. Exclusive feature. Story + Post + Reel. #IslamvyRamadan. Affiliate 30%. 3 gun post | 500 | 70K indirme
15 | 02-Mar | Hafta 2 Scale | TikTok Ads | Viral Boost | TikTok Ads Manager. Spark Ads UGC kullan. In-Feed native. Butce 30$/gun. 18-35 Muslim. Dream interpretation hook. Comment engage | 30 | 90K indirme
16 | 03-Mar | Hafta 2 Scale | Cross-Promo | Partner Anlas | 5 Islamic app gorusme. Banner exchange. Newsletter swap. Co-marketing. Bundle: Best Islamic Apps. Affiliate link. Social shoutout | - | 110K indirme
17 | 04-Mar | Hafta 2 Scale | Week Review | ROI Check | Ads dashboard: platform CPI. Best creative. Geographic winners. Influencer ROI who delivered. Butce reallocation. Hafta 3 scale plan. 100K milestone | - | 130K indirme
18 | 05-Mar | Ramadan Prep | Feature Launch | Ramadan Update | App update: Ramadan features. Oruc tracker tanit. Iftar/Sahur alarms. Blog: Digital Ramadan Companion. Press release. Email existing users. Push: New features | - | 150K indirme
19 | 06-Mar | Ramadan Prep | Campaign Start | #30DaysIslamvy | Hashtag kampanya. Daily challenge 30 gun plan. Influencer brief. Prize: 3 iPhone 30 Premium. Landing page. Email funnel. Countdown timer | 200 | 175K indirme
20 | 07-Mar | Ramadan Prep | Content Blitz | Ramadan Series | YouTube: Ramadan with Islamvy series. TikTok: Sahur alarm. IG: Iftar countdown. Twitter: Ramadan tips. Blog: Tech in Ramadan. 5 podcast. Local TV pitch | - | 200K indirme
21 | 08-Mar | Ramadan Prep | Ad Scale Up | Butce 2x | FB 20→40$/gun. Google 15→30$/gun. TikTok 30→60$/gun. Apple 10→20$/gun. Ramadan creative. Lookalike genislet. Retargeting baslat | 150 | 240K indirme
22 | 09-Mar | Ramadan Prep | Community Event | Mega Hatim | 1 Million Prayers hatim announce. Auto-assignment. Live counter web. Influencer hatim lideri. Daily progress. Completion charity. Press: Largest digital hatim | - | 280K indirme
23 | 10-Mar | Ramadan Prep | PR Mega Push | Medya Patlama | 50 outlet press. TV interview 10 kanal. Radio 15 istasyon. Podcast tour. Founder AMA schedule. Tech media exclusive BTS. User testimonial 10 video | - | 330K indirme
24 | 11-Mar | Ramadan Prep | Week Review | Final Check | Ramadan features test. Server capacity peak. Notification timing verify. Payment stress test. Influencer calendar final. Ad campaigns review. Team prep | - | 400K indirme
25 | 12-Mar | RAMADAN GUN 1 | Launch Day | Karsilama | 05:00 Sahur push global. 06:00 Ramadan Mubarak social. 08:00 First iftar countdown. 10:00 Special hatim acilis. 13:00 Influencer wave. 17:00 Iftar reminder. 20:00 Daily quote. 22:00 Metrics 100K new | - | 500K indirme
26 | 13-Mar | RAMADAN GUN 2 | Momentum | Organic Boom | UGC repost 50x. Trending hashtag join. Daily iftar notify. Community contest. Viral challenge Best setup. Influencer stories track. Real-time engage. Ad stable | 150 | 630K indirme
27 | 14-Mar | RAMADAN GUN 3 | Scale | Paid Turbo | Ad butce 3x temp. Lookalike genislet. Ramadan keywords bid artir. Influencer round 2 pay. Viral boost. Retargeting aggressive. CPI 0.50 alti | 450 | 800K indirme
28 | 15-Mar | RAMADAN GUN 4 | Media Wave | TV & Radio | TV interviews 5x. Radio show 5x. Newspaper interview. Tech blog features publish. Podcast episodes live. Press coverage track. Earned media ROI | - | 950K indirme
29 | 16-Mar | RAMADAN GUN 5 | Viral Peak | 1M Milestone | 1 MILLION announcement. Thank you video. Giveaway 10 iPhone. Influencer shoutout wave. Media success story. Community celebration. Premium flash 24h discount | 100 | 1.1M indirme
30 | 17-Mar | RAMADAN GUN 6 | Sustain | Devam | Daily content continue. Engagement optimize. Retention focus. Premium conversion push. Community moderation guclendir. Bug fixes fast. Support scale | 150 | 1.25M indirme
31 | 18-Mar | RAMADAN GUN 7 | Week Review | Analiz | Week-over-week growth. Retention Day 7. Premium conversion rate. Churn analysis. Top content. Influencer ROI final. Hafta 5 tweak | 150 | 1.4M indirme
32 | 19-Mar | Ramadan Hafta 2 | Consistency | Daily Grind | Sahur notify iftar countdown community engage viral share ad optimize influencer checkin | 150 | 1.55M indirme
33 | 20-Mar | Ramadan Hafta 2 | Feature Push | AI Showcase | AI Dream showcase viral success stories user testimonials premium highlight | 150 | 1.7M indirme
34 | 21-Mar | Ramadan Hafta 2 | Community | UGC Amplify | User contest results top creators spotlight leaderboard hatim celebration | 150 | 1.85M indirme
35 | 22-Mar | Ramadan Hafta 2 | Partnership | Islamic Brands | Islamic fashion brands Muslim business collabs charity orgs co-marketing | 100 | 2M indirme
36 | 23-Mar | Ramadan Hafta 2 | Retargeting | Conversion | Lapsed user reengagement email winback push test premium trial | 150 | 2.15M indirme
37 | 24-Mar | Ramadan Hafta 2 | Viral Stunt | Mega Challenge | #IslamvyMillionPrayers celebrity involvement charity tieup media coverage | 200 | 2.35M indirme
38 | 25-Mar | Ramadan Hafta 2 | Week Review | Deep Dive | DAU trend session length feature heatmap revenue tracking retention cohorts | 150 | 2.5M indirme
39 | 26-Mar | Ramadan Hafta 3 | Qadr Prep | 10 Son Gece | Last 10 nights feature ibadah tracker midnight notify exclusive content | 150 | 2.65M indirme
40 | 27-Mar | Ramadan Hafta 3 | Ad Blitz | Max Spend | Butce 5x son push all platforms best creatives CPI optimize | 750 | 2.85M indirme
41 | 28-Mar | Ramadan Hafta 3 | Influencer Final | Celebrity | Top-tier deals celebrity endorsements sports personalities viral moment | 1000 | 3.1M indirme
42 | 29-Mar | Ramadan Hafta 3 | PR Finale | Success Story | 3M Muslims Connected press founder interviews major media push | - | 3.25M indirme
43 | 30-Mar | Ramadan Hafta 3 | Community Peak | Million Prayer | 1M prayers achieved charity donation user thankyou viral moment | 100 | 3.4M indirme
44 | 31-Mar | Ramadan Hafta 3 | Flash Sale | Premium Push | 50% Premium 48h scarcity countdown conversion optimize | 50 | 3.55M indirme
45 | 01-Apr | Ramadan Hafta 3 | Week Review | Final Sprint | Are we hitting 3M gap analysis emergency tactics if behind sustain if ahead | 150 | 3.7M indirme
46 | 02-Apr | Ramadan Hafta 4 + Eid | Eid Prep | Hazirlık | Eid feature teaser post-Ramadan retention Eid content prep | 150 | 3.85M indirme
47 | 03-Apr | Ramadan Hafta 4 + Eid | Laylat Qadr | Peak Night | Special notification exclusive content live events | 150 | 4M indirme
48 | 04-Apr | Ramadan Hafta 4 + Eid | Last Days | Finale | Ramadan finale nostalgia thankyou messages | 150 | 4.15M indirme
49 | 05-Apr | Ramadan Hafta 4 + Eid | Eid Launch | Go Live | Eid Mubarak feature greeting cards community wishes | 150 | 4.3M indirme
50 | 06-Apr | Ramadan Hafta 4 + Eid | Eid Day | Celebration | Mass greetings viral Eid content celebration stories | 200 | 4.5M indirme
51 | 07-Apr | Ramadan Hafta 4 + Eid | Post Eid 1 | Sustain | Daily worship tools habit formation retention | 100 | 4.6M indirme
52 | 08-Apr | Ramadan Hafta 4 + Eid | Post Eid 2 | Optimize | Engagement metrics premium push feature discovery | 100 | 4.7M indirme
53 | 09-Apr | Ramadan Hafta 4 + Eid | Post Eid 3 | Retention | User journey optimize onboarding improve DAU focus | 100 | 4.8M indirme
54 | 10-Apr | Ramadan Hafta 4 + Eid | Week Review | Analysis | Full campaign review ROI calculation lessons learned scale plan | 100 | 4.9M indirme
55 | 11-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 4.9M indirme
56 | 12-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 4.9M indirme
57 | 13-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
58 | 14-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
59 | 15-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
60 | 16-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
61 | 17-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
62 | 18-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
63 | 19-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
64 | 20-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
65 | 21-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
66 | 22-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
67 | 23-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
68 | 24-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
69 | 25-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
70 | 26-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
71 | 27-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
72 | 28-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
73 | 29-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
74 | 30-Apr | Post-Ramadan | Retention Mode | DAU Sustain | Focus: daily active retention premium conversion feature discovery habit building community engagement | 100 | 5.0M indirme
75 | 01-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
76 | 02-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
77 | 03-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
78 | 04-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
79 | 05-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
80 | 06-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
81 | 07-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
82 | 08-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
83 | 09-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
84 | 10-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
85 | 11-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
86 | 12-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
87 | 13-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
88 | 14-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
89 | 15-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
90 | 16-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
91 | 17-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
92 | 18-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
93 | 19-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
94 | 20-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
95 | 21-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
96 | 22-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
97 | 23-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
98 | 24-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme
99 | 25-May | Long-term | Steady Growth | Optimize | LTV maximize referral loop content calendar community management analytics review | 75 | 5M+ indirme

## Ozet Metrikler
ISLAMVY 99 GUN KAMPANYA OZETI
FAZ | GUNLER | HEDEF INDIRME | TOPLAM BUTCE
Lansman Hazirlik | -7 to 0 | 0 | $13
Lansman | 0-3 | 5,000 | $150
Ilk Hafta | 4-10 | 35,000 | $20
Hafta 2 - Scale | 11-17 | 130,000 | $575
Hafta 3 - Ramadan Prep | 18-24 | 400,000 | $200
Hafta 4 - Ramadan Start | 25-31 | 1,400,000 | $1,000
Ramadan Hafta 2-4 | 32-54 | 4,900,000 | $4,700
Post-Ramadan | 55-99 | 5,000,000+ | $3,800
TOPLAM | 99 gun | 5,000,000

## Acilacak Hesaplar
BUGUNDEN ACILACAK ALINACAK HER SEY
PLATFORM | HANDLE DETAY | MALIYET | DURUM
Instagram | @islamvy.app @islamvy.tr @islamvy.ar @islamvy.id | Free | GUN -6
TikTok | @islamvyapp tum diller | Free | GUN -6
Twitter X | @islamvyapp | Free | GUN -6
YouTube | Islamvy Official | Free | GUN -6
Canva Pro | Design tool | $13/ay | GUN -5
Product Hunt | Launch | Free | GUN -2
Firebase | Analytics | Free tier | GUN -1
Adjust Appsflyer | Attribution | Free tier | GUN -1
Facebook Ads | Manager | Free | GUN 11
Google Ads | UAC | Free | GUN 12
Apple Search Ads | Campaign | Free | GUN 13
TikTok Ads | Business | Free | GUN 15
Telegram | Community | Free | GUN 5
Discord | Server | Free | GUN 5
Medium | Blog | Free | GUN 3
LinkedIn | Company page | Free | GUN 2